## Slide 1
Transportation Committee| February 28, 2018
Northside Pedestrian Bridge
MAYOR KEISHA LANCE BOTTOMS | WILLIAM M. JOHNSON, COMMISSIONER

## Slide 2: BACKGROUND INFORMATION
Legislation was approved July 18, 2016, authorizing the execution of a design-build contract for a pedestrian bridge.
The original contract was to be performed in two phases, with a total project cost up to $23.2M.
Phase 1: Cost allocation for $17.4M
Phase 2: Cost allocation for an additional $4.8M
The original legislation authorized $12.89M of Phase 1, based on immediate availability.
*Legislation was amended to require Council approval for funding the remaining project allocation.
Notes: · Supported the Mayor’s Office of Constituent Services warming center operations by providing staffing and logistical support
·
Demonstrated compliance for 18 of 18 Emergency Preparedness practices during the Department’s American Public Works Association accreditation process
Implemented a Level 3 Response activation for winter weather event, January 6-9, 2018
Supported the City’s College Football Championship (CFC) operations by providing DPW staff support at the Joint Operations Center (JOC); nine team members
Maintained clear ROWs and sidewalks throughout the downtown corridor during the CFC
Served as lead agency in Unified Command at the City’s JOC for the January 15-18 winter weather event

## Slide 3: Northside pedestrian bridge Project rendering

## Slide 4: PROJECT EXPENDITURES TO DATE
APPROVED ALLOCATION | PAID TO DATE
$2,000,000.00 | 
$6,890,254.00 | $4,390,254.00
 | $2,500,000.00
$4,000,000.00 | $4,000,000.00
$12,890,254.00 | $10,890,254.00

## Slide 5: Northside pedestrian bridge
Exterior View: Looking East to West

## Slide 6
Approximately $13M has been invoiced to date for the project.
Of the $13M invoiced, approximately $3M is for materials ordered for Phase 2 (Skin required up to one year lead time).
Actuals paid to date: $10.8M.
Remaining allocation to be approved by Council: $12.2M.
*Due to delays in the demolition of the GA Dome and negotiations of air rights, long lead materials were ordered to meet construction schedules.
REMAINING COSTS

## Slide 7: Northside pedestrian bridge
View from Inside the Enclosed Section

## Slide 8
TIMELINE MOVING FORWARD
Final authorization for project funding allocation as defined in the contract
Anticipated final approval by March 19, 2018
Internal and external stakeholder site visit: March 2018
Revised project completion date: November 2018