## Slide 1: Renew Atlanta Bond Program: Roadway Resurfacing
Amanda Noble, City Auditor
Stephanie Jackson, Deputy City Auditor
Bradford Garvey, Audit Manager
Matthew Ervin and Amber Hart, Performance Auditors
November 29, 2017

## Slide 2: Renew Atlanta Roadway Resurfacing
$1 billion infrastructure backlog (01/ 2015)
Citizens approved $250 million Renew Atlanta Infrastructure bond. (03/2015)
  Transportation projects — $184.1 million
  Facility projects — $65.9 million
Over $27 million for roadway resurfacing

## Slide 3: Objectives of Audit
Is the Renew Atlanta program managing the roadway resurfacing projects according to the Program Management Plan and best practice?
Were the payments made by the Renew Atlanta Program to the roadway resurfacing contractors appropriately supported and allowable under the contract?

## Slide 4: Scope of Audit
84 streets resurfaced under two contracts
  FC-6945
    Originally a DPW contract
    Stewart Brothers, Inc.
    $10 million in Renew Atlanta funds added in July 2015
  FC-8831
    Over $14 million, executed August 2016
    Joint venture of Stewart Brothers, Inc. and HEH Paving, Inc.
Resurfacing projects undertaken from July 2015-January 2017

## Slide 5: Methodology
Reviewed contracts
Interviewed Renew Atlanta and other city staff
Reviewed and reconciled financial data from Oracle and Renew Atlanta
Took a sample of 33 streets to cover:
  20% of amount paid on FC-6945 (17 streets)
  All work done in specified timeframe under FC-8831 (16 streets)
Reviewed supporting documents related to our sample of 33 streets

## Slide 6: Project Control Board Authorization
Program Management Plan created Project Control Board
Board authorizes projects at key stages
  Preliminary design
  Closeout
No preliminary design authorization for 56 out of 84 streets
No closeout authorization for any streets

## Slide 7: Inconsistent Documentation Leads to Unfunded Work
Five resurfaced streets never had PO, so never had funds encumbered
Insufficient encumbrance for additional group of streets (below)
Insufficient encumbrance for increased scope for three more streets

## Slide 8: Supporting Documentation for Amounts Billed
Sample of 33 streets—about $3 million paid
Approximately $1 million of line items lacked sufficient support
The lack of support was almost entirely for work under FC-6945
Significant improvement in documentation for later work under FC-8831

## Slide 9: Overpayment for Mobilization
Contracts stipulated only one mobilization payment for nearby projects on same purchase order
Contracts stipulated no mobilization payment when total value of nearby projects >$250 million
Overpayment of $187,500

## Slide 11: Controls Are in Place to Mitigate Risks
Inherent risks are mitigated by original documents and multiple layers of review
Standard operating procedures manual in place as of April 2017

## Slide 12: Renew Atlanta Lacks Document Management System
PMP relies on document management and information technology system to implement controls and for internal communication
Renew Atlanta not using ORION system
New system, eBuilder, not in place yet
Lack of document management solution:
  Impairs ease of communication
  Introduces risk of permanent destruction of records
  Reduces feasibility of using automated controls

## Slide 13: Project Control Board Recommendations
Present preliminary design PIPs for all projects, including new projects and ongoing or finished projects
Report variances over the threshold defined by the program management plan to the Project Control Board
Present closeout PIPs for completed projects

## Slide 14: Recommendations to Ensure Sufficient Encumbrances
Develop a process to ensure that procurement creates a purchase order and funds are encumbered in Oracle before contractors begin work or complete an increased scope of work
Regularly reconcile Oracle budgets and encumbrances, Project Control Board documents, and internal financial documentation

## Slide 15: Recommendations to Ensure Payments are Appropriate
Take steps to ensure that the contractors are generating and maintaining all documentation required by the contracts
Continue to require sufficient supporting documentation as a precondition for payment, as has been done on work performed more recently
Work with the Department of Law to pursue cost recovery for potential overpayments to contractors

## Slide 16: Recommendations to Ensure Integrity of Information
Complete implementation of an electronic document management system and ensure the system contains all necessary documentation.

## Slide 17: Questions?